## Regular PRD Issues & New Develp
SL NO | Business user | Module | Date of mail Recived for development | Development Start Date | Completion Date at Development | Object Desccription | Object | Object Type | Benefits | Details | Development Type | API Call | Status | Transport Request | System | Package | TR status | Date of Mail for TR to quality | Person Worked
1 | Ashish Kumar | SD |  | 2025-06-25 | 2025-06-27 |  | ZSD101 | Tcode | BRS Upload | Here they can upload the BRS details into custom Table. Copyb program from UNO MINDA system to ROKI MINDA. | NEW Development | no | DONE | D03K902524 MINDA07 SD:ZSD101:BRS Upload:26.06.2025 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
2 | Ashish Kumar | SD |  | 2025-06-25 | 2025-06-27 |  | ZSD101A | Tcode | E-Way Bill Uploading Program | Here they can upload the E-Way Bill details into custom Table. | NEW Development | no | DONE | D03K902526 MINDA07 SD:ZSD101A:E-Way Bill Uploading Program:26.06.2025 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
3 | Ashish Kumar | SD |  | 2025-06-25 | 2025-06-27 |  | ZSD102 | Tcode | ENAGARE Update |  | NEW Development | no | DONE | D03K902528 MINDA07 SD:ZSD102:ENAGARE Update:26.06.2025 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
4 | Ashish Kumar | SD |  | 2025-06-25 | 2025-06-27 |  | ZSD103 | Tcode | MSIL ENAGARE ALV |  | NEW Development | no | DONE | D03K902530 MINDA07 SD:ZSD103:MSIL ENAGARE ALV:26.06.2026 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
5 | Anuj Kukreja | SD |  | 2025-06-26 | 2025-06-27 |  | ZTSD_PRODUCTLINE | Table | Product Line Details | Here user can strore Product Line I details | NEW Development | no | DONE | DEVK947020 9000RUPESH S 8000015797: SD:3 tables:Prdt line, family & Product | UNO MINDA | ZSD01 | QAS | 2025-08-13
6 | Anuj Kukreja | SD |  | 2025-06-26 | 2025-06-27 |  | ZTSD_PRDTFAMILY | Table | Product Line Family Details | Heare user Can Create Product Line Family Details . | NEW Development | no | DONE | DEVK947020 9000RUPESH S 8000015797: SD:3 tables:Prdt line, family & Product | UNO MINDA | ZSD01 | QAS | 2025-08-13
7 | Anuj Kukreja | SD |  | 2025-06-26 | 2025-06-27 |  | ZTSD_PRODUCT | Table | Product Details | Here user can crete Product Details. | NEW Development | no | DONE | DEVK947020 9000RUPESH S 8000015797: SD:3 tables:Prdt line, family & Product | UNO MINDA | ZSD01 | QAS | 2025-08-13
8 | Rupesh Chauhan | PP | 2026-06-26 |  | 2025-06-30 |  | ZGW_PP_ROUTING_DETAIL | ODATA Project | Routing Details | Here for getting routing details user no need to check multiple Tables ,as well as we can show SAP routing Details in outside SAP system Thouth ODATA API call. | NEW Development | GET | DONE | DEVK947001 9000RUPESH S 8000015789: PP:ODATA:SAP Routing Details | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | DEBI
9 | Ashish Kumar | SD |  | 2025-06-30 | 2025-07-01 |  | ZSD182 | TCode | Sales Order Approval | Here I had done changes in the mail body content | Modification | no | DONE | DEVK946414 DEVELOPER Sale Order Approval Process | UNO MINDA | ZSD01 | dev
10 | Ashish Kumar | SD |  | 2025-06-30 | 2025-07-01 |  | VA01(User exit-include) | Tcode | Sles Order Creation time Enhacement(SAPMV45A-MV45AF0C_CHANGE_DOCUMENT_CREAT) | When any Sales order creted, a mail related to approval should go to the concern person and for that mail alredy enhacement done , only I chaged the mail body in the user exit 's include. | Modification | No | DONE | DEVK946414 DEVELOPER Sale Order Approval Process | UNO MINDA | VA | dev
11 | Siddharth Tiwari | FI |  | 2025-07-01 | 2025-07-02 |  | ZFI161 | TCode | GST Inward Register | Here additional field l added in the report along with some regular correction. | modification | No | DONE | DEVK947055 9000RUPESH S 8000015833: FI:ZFI161:BUG Fixing & adding New field | UNO MINDA | ZSANTHUDEV | Dev->QAS | 2025-07-02
12 | Rajan singh | MM |  | 2025-07-02 | 2025-07-03 |  | QI01(include-MQBAAF13) | Tcode | Crete Q-info record Validation for Vendor (ZQM_NBH_CHECK-MQBAAF13) | Check the validatiomn for Vendor Based On LIFNR-GENT field , after thet check the vandor validation field value "vldat", if today's date id grater then validation date then we will block the vendor and raise error message. | Modification-Enhacement | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA | QB | QAS | 2025-07-08
13 | Rajan singh | MM |  | 2025-07-02 | 2025-07-03 |  | ME11(Include-MM06IF01_BUCHEN) | TCode | Crete infor record Initial Screen Validation For Venndor(MM06IF01_BUCHEN) | Check the validatiomn for Vendor Based On LIFNR-GENT field , after thet check the vandor validation field value "vldat", if today's date id grater then validation date then we will block the vendor and raise error message. | Modification-Enhacement | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA | ME | QAS | 2025-07-08 | SHIVANSH
14 | Rajan singh | MM |  | 2025-07-02 | 2025-07-03 |  | ME31L(Include- ZXM06U43) | Tcode | Create Scheduling Aggrement:initial Screen Validation for Vandor(ZXM06U43) | Check the validatiomn for Vendor Based On LIFNR-GENT field , after thet check the vandor validation field value "vldat", if today's date id grater then validation date then we will block the vendor and raise error message. | Modification-Enhacement | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA | ZHANA | QAS | 2025-07-08 | SHIVANSH
15 | Rajan singh | MM |  | 2025-07-02 | 2025-07-03 |  | Me21n,me22n(ZCL_IM_6_PO_CUST_CHK -- IF_EX_ME_PROCESS_PO_CUST~CHECK) | Tcode | Purchase order Cretion Time Vandor Validation (IF_EX_ME_PROCESS_PO_CUST~CHECK) | Check the validatiomn for Vendor Based On LIFNR-GENT field , after thet check the vandor validation field value "vldat", if today's date id grater then validation date then we will block the vendor and raise error message. | Modification-Enhacement | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA | ZMM01 | QAS | 2025-07-08
16 | Rajan singh | MM |  | 2025-07-02 | 2025-07-04 |  | BP | Tcode | BP Creation Time Validationm for ZGNET value N or E | Check the validation for Vendor Based On LIFNR-GENT field , If the field is 'N' & 'E' then it will check the mandatory field NBH Reason and Valid to date.if those field value is initial then it will raise error message. | Modification-Enhacement | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA | Z001 | QAS | 2025-07-08 | SHIVANSH
17 | Rajan singh | MM |  | 2025-07-02 | 2025-07-04 |  | BP | Tcode | Bp Screen Field name changes | BUPT----> BUSINESS PATNER---> SCREEN LAYOUT--> BUS3(VIEW)--> View name(ZVEN00)--> Program name (SAPLCVI_FS_UI_VENDOR)--> Screen Painter | Screen Modification | no | DONE | DEVK947077 9000RUPESH S 8000015850: MM: NBH Development Correction | UNO MINDA |  | QAS | 2025-07-08
18 | Rajan singh | MM |  | 2025-07-02 | 2025-07-04 |  | ZMM118 | TCode | Vendor Report Field Name Changes | Accoding to user The field name is modified | Modification | no | DONE | DEVK946875 DEVELOPER NBH | UNO MINDA | ZSANTHUDEV | QAS | 2025-07-08
19 | Ashish Kumar | SD |  | 2025-07-04 | 2025-07-04 |  | ZSD105 | TCode | ENAGARE DELETE Process | Copy Program | NEW Development | NO | DONE | D03K902532 MINDA07 SD:ZSD105:ENAGARE DELETE:04-07-2025 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
20 | Ashish Kumar | SD |  | 2025-07-04 | 2025-07-04 |  | ZSD106 | Tcode | ENAGARE DETAILS Report | Copy Program | NEW Development | NO | DONE | D03K902534 MINDA07 SD:ZSD106:ENAGARE DETAILS Report:04-07-2025 | ROKIMINDA | ZSD01 | QAS | 2025-07-07
21 | Sanjeev Kumar | SD |  | 2025-07-04 | 2025-07-04 |  | ZSD139 | Tcode | Spool file SUZUKI moters | Concatenate Billing document number with Downloading Location URL | Modification | NO | DONE | DEVK947118 ABAP S 8000015872: SD: ZSD139-Spool file name change | UNO MINDA | ZSANTHUDEV | QAS | 2025-07-08 | SHIVANSH
22 | Rupesh Chauhan | PP |  | 2025-06-25 | 2025-07-04 |  | ZGW_PP_PRODUCTION_VERSION | ODATA Project | Production Version Details | Provided GET API to fetch Production Version Details. | NEW Development | GET | DONE | DEVK947047 9000RUPESH S 8000015826: PP:ODATA:SAP Production Version Detail | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | DEBI
23 | Rupesh Chauhan | PP |  | 2025-07-04 | 2025-07-09 |  | ZGW_PP_PRODUCTION_ORDER | ODATA Project | Production Order Details | Provided GET API to fetch Production Order Details Along with Get the Routing & component Details per production Order. | NEW Development | GET | DONE | DEVK947147 9000RUPESH S 8000015885: PP:ODATA:SAP Production Order Details | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | DEBI
24 | Rajan Singh | MM |  | 2025-07-08 | 2025-07-08 |  | Me21n,me22n(ZCL_IM_6_PO_CUST_CHK -- IF_EX_ME_PROCESS_PO_CUST~CHECK) | Tcode | invalid vandor,Block the vandor related Sales Organization | In the PO if Valdor is invalid based on the NBH Valid to date , thenall the sales organization for the vandor must be blocked. | Modification-Enhacement | no | DONE | DEVK947161 9000RUPESH S 8000015894: MM:NBH Vendor Block on Purchase Org. | UNO MINDA |  | QAS | 2025-07-09
25 | Rajan Singh | MM |  | 2025-07-08 | 2025-07-08 |  | ME31L,ME32L(Include- ZXM06U43) | Tcode | invalid vandor,Block the vandor related Sales Organization | In the PO if Valdor is invalid based on the NBH Valid to date , thenall the sales organization for the vandor must be blocked. | Modification-Enhacement | no | DONE | DEVK947161 9000RUPESH S 8000015894: MM:NBH Vendor Block on Purchase Org. | UNO MINDA |  | QAS | 2025-07-09
26 | Rajan Singh | MM |  | 2025-07-08 | 2025-07-08 |  | ME11(Include-MM06IF01_BUCHEN) | Tcode | invalid vandor,Block the vandor related Sales Organization | In the PO if Valdor is invalid based on the NBH Valid to date , thenall the sales organization for the vandor must be blocked. | Modification-Enhacement | no | DONE | DEVK947161 9000RUPESH S 8000015894: MM:NBH Vendor Block on Purchase Org. | UNO MINDA |  | QAS | 2025-07-09
27 | Rajan Singh | MM |  | 2025-07-08 | 2025-07-09 |  | ZGATE | Tcode | invalid vandor,Block the vandor related Sales Organization | In the PO if Valdor is invalid based on the NBH Valid to date at the time of Gate Entry , then all the sales organization for the vandor must be blocked. | Program Modification | no | DONE | DEVK947161 9000RUPESH S 8000015894: MM:NBH Vendor Block on Purchase Org. | UNO MINDA |  | QAS | 2025-07-09
28 | Vibhuti Praksd | FI |  | 2025-07-10 | 2025-07-10 |  | ZCIJ_CATEGORY | Domain | Adding new filter value in Domain value range | Adding new filter value in Domain value range | Domain Modification | no | DONE | DEVK947184 ABAP S 8000015908: FICO: CIJ Category Addition | UNO MINDA |  | QAS | 2025-07-10 | SHIVANSH
29 | Rajan singh | MM |  | 2025-07-10 | 2025-07-14 |  | Z6MM_INV_EMAIL | Report | Mail will trigger to Authorized Person based on the Stuck Quantity. | I have added an Other level of approver Details and now the data will fetched in range days based on Status | Modification | NO | DONE | DEVK947165 ABAP S 8000015899: MM: Inventory Norms Revised - FG & WI | UNO MINDA |  | QAS | 2025-07-24 | SHIVANSH
30 | Rupesh Chauhan | PP |  | 2025-07-10 | 2025-07-14 |  | ZGW_PP_PRDC_CONF_WITHOUT_MPN | ODATA Project | Production Order Confirmation Without MPN | User can send a production order confirmation without MPN Create Send Request from Outside SAP Application and based on the Request, it will crete record in SAP System. | NEW Development | POST | DONE | DEVK947192 9000RUPESH S 8000015910: PP:ODATA: Production Conf. Without MPN | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
31 | Rupesh Chauhan | PP |  | 2025-07-14 | 2025-07-18 |  | ZGW_PP_PRDC_ORD_TRANS_POSTING | ODATA Project | Transfer Posting | User can send Material tranfer posting from outside SAP system and based on the request it will create record in SAP System. | NEW Development | POST | DONE | DEVK947217 9000RUPESH S 8000015929: PP:ODATA:Production Order TransferPostig | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
32 | Rupesh Chauhan | PP |  | 2025-07-21 | 2025-07-24 |  | ZGW_PP_BOM_DETAIL | ODATA Project | BOM Master Details | User can able tho see the BOM details along | NEW Development | GET | DONE | DEVK947283 9000RUPESH S 8000015973: PP:ODATA: Bill Of Material(BOM) Details | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
33 | Sanjeev Kumar | SD |  | 2025-07-24 | 2025-07-25 |  | ZSD101(ZENAGARE_UPLOAD) | Tcode | BRS Upload | To resolve the Quality issue I changed the OLD function module "WS_UPLOAD" with a new fuction module 'TEXT_CONVERT_XLS_TO_SAP' | Modification | no | DONE | D03K902539 MINDA07 SD:ZSD101:Upload Function Module Correction | ROKIMINDA | zsd01 | dev
34 | Rupesh Chauhan | MM |  | 2025-07-28 | 2025-07-31 |  | ZGW_MM_MATERIAL_MASTER_DETAIL | ODATA Project | Material Master Details | User Can able to See Material Master details outside of SAP Server/System | NEW Development | GET | DONE | DEVK947359 9000RUPESH S 8000016007: MM:ODATA: Material Master Details | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
35 | Sanjeev Kumar | SD |  | 2025-07-31 |  |  | VL02N,ZSD022 | Tcode | Change Otbound delivery Vaidation,B.O.L/L.R.No. Upload Description Chage | Foe VL02N Tcode Validation I chaged the previous validation used in Standared Include "MV50AfZ1" check link number-1806 and added the extra validation as per FS | Enhacement Modification,Attribute section description chage | no | DONE | DEVK947417 9000RUPESH S 8000016051: SD:Rstrct to edit delivery aftr gate out | UNO MINDA |  | QAS | 2025-08-04
36 | Sunil Kumar | PP |  | 2025-08-06 | 2025-08-08 |  | ZGW_PP_PRODUCTION_GOODS_ISSUE | ODATA Project | Production Goods Issue | User can issue the goods against Production order from Outside SAP System | NEW Development | POST | DONE | DEVK947507 9000RUPESH S 8000016113: PP:ODATA:Production Goods Issue | UNO MINDA | ZSANTHUDEV |  | 2025-12-10
37 | Rajan singh | MM |  | 2025-08-08 |  |  | ZMM_WIP_INVENTORY_NORMS | REPORT | Inventory Norms WIP Email Notification | Email handling based on Inventory days to Different level of Business Users. | NEW Development | NO | DONE | DEVK947412 ABAP S 8000016046: Inventory Norms Email Notif_V2_31.07.25 | UNO MINDA |  |  |  | SHIVANSH
38 | Rajan singh | MM |  | 2025-07-31 |  |  | BP | Tcode | At the time of extending indian Vendor , GST & PAN number is the Mandatory field. | Business logic : ZCL_IM_BP_CHECK_AT_SAVE IF_EX_BUPA_GENERAL_UPDATE~CHANGE_BEFORE_UPDAT | Enhacement Modification | no | Discarded(20-11-2025) | DEVK947421 9000RUPESH S 8000016056: MM:BP:PAN & GST No. Validation | UNO MINDA |  |  |  |  | Discarded
39 | Sanjeev Kumar | sd |  | 2025-08-13 | 2025-08-13 |  | MV50AFZ1 | Enhacement-include |  | MV50AFZ1 | Retrival of OLD Version | no | DONE | DEVK947593 9000RUPESH S 8000016164: SD:Delivery Correction | UNO MINDA |  | QAS | 2025-08-13
40 | Sanjeev Kumar | sd |  | 2025-08-14 | 2025-08-18 |  | MV50AFZ1 | Enhacement-include | When deleivery completed we have to restrict the user to edit. | MV50AFZ1 | Enhacement Modification | no | DONE | DEVK947603 9000RUPESH S 8000016170: SD:Rstrct edit deliv aftr gate out NEW | UNO MINDA |  | QAS | 2025-08-18
41 | Sunil Kumar | MM |  | 2025-08-13 | 2025-08-19 |  | ZGW_MM_BATCH_MANAGEMENT | ODATA Project | SAP Batch management DATA | End user can access Material Batch details outside of SAP Environment. | NEW Development | GET | DONE | DEVK947589 9000RUPESH S 8000016162: MM:ODATA:Batch Management Data | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
42 | Wajid Chaudhury | MM |  | 2025-08-25 | 2025-08-27 |  | ZGW_MM_MIGO_DETAILS | ODATA Project | SAP MIGO Data | End user can access SAP MIGO Data outside of SAP Environment. | NEW Development | GET | DONE | DEVK947680 9000RUPESH S 8000016221: MM:ODATA:MM:MIGO Details | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10
43 | Rajan singh | MM |  | 2025-08-26 | 2025-08-26 |  | ZMM_PO_RELEASE_ESCALATION | Report | during program execution ,System should ignore the Delivery completed line item which fatching record from Ekpo | User only get the PO number in mail of those PO whose PO are partially complete delivery and Not deleted | Modification | no | DONE | DEVK947694 9000RUPESH S 8000016229: MM:Retrive PRD Vrsn & Ignore Delivr Item | UNO MINDA |  | QAS | 2025-09-10
44 | Siddharth Tiwari | fi |  | 2025-08-28 |  |  | ZFI161 | Tcode | User will able to get the HSN_SAC detail in every line item Level. | Previously for HSN_SAC we depend upon BSEG table due to which some item level it was not mainted against Material .but not we are conidering from MARC table based on material and Plant ,due to which if a line item cintain material, then that HSN_SAC field will be filled as per my logic written to fetch from MARC. | Modification | no | Discarded(3-12-2025) | DEVK947708 9000RUPESH S 8000016251: FICO: ZFI161 report correction - 28.8 | UNO MINDA |  | DEV |  | Debidutta
45 | vivek Mishra | MM |  | 2025-09-03 | 2025-09-03 |  | me21n & me22n ( ME_PROCESS_PO_CUST --> ZCL_IM_6_PO_CUST_CHK--> checck Method) | Enhacement-CLASS & Method | User can creted a PO Smoothly. | Previously when user want to update an po item level delivery date,that date must be in future compare to PO header level cretion date,so I updated the logic and compared item level delivery daye with po header level cretion date and resolve the issue. | Modification | no | DONE | DEVK947750 9000RUPESH S 8000016276: MM:PO date change Logic | UNO MINDA |  | QAS | 2025-09-03
46 | Wajid Chaudhury | MM |  | 2025-09-10 | 2025-09-11 |  | Z6MM0075_SF_GRN_STICKER_PRINT | Smartform Changes | User will get correct level value In sticker | Previously the Level no 1 hard coded in the smartform level, I chaged it and make it dynamic as per the level no getting from the backebd. | Modification | no | DONE | DEVK947823 ABAP S 8000016312: ZGRN_R_BARCODE_LABLE_ISSUE_10_09_2025 | UNO MINDA |  | QAS | 2025-09-15
47 | Rajan singh | mm |  | 2025-09-16 | 2025-09-16 |  | ZMM0065 | TCode | Added new fiels of NBH of Vendor in Report | User can able to chedck the NBH Data in report | Modification | No | DONE | DEVK947869 :MM:ZMM065:Added new Fields NBH Block | UNO MINDA |  | QAS | 2025-10-09
48 | Wajid Chaudhury | MM |  | 2025-09-01 | 2025-09-08 |  | ZGW_MM_VENDOR_MASTER_DETAIL | ODATA Project | SAP Vendor Master Data | End User Can Access SAP Vendor Master Data from Outside SAP Environment. | NEW Development | GET | DONE | DEVK947733 9000RUPESH S 8000016264: MM:ODATA:Vendor Mater Details | UNO MINDA | ZSANTHUDEV | DEV
49 | Sunil Kumar/Ashish Kumar | SD |  | 2025-03-12 | 2025-09-17 |  | ZGW_SD_DELIVERY_DETAILS | ODATA Project | SAP Delivery Master Data | End User can access SAP delivery Master Data Outside SAP | NEW Development | GET | DONE | DEVK947845 9000RUPESH S 8000016327: SD:ODATA:Delivery Master Data | UNO MINDA | ZSANTHUDEV | dev
50 | Rajan singh | MM |  | 2025-09-18 | 18-09-2025` |  | ME11(Include-MM06IF01_BUCHEN --ENHANCEMENT 1 ZMM_ME11_12_NBH_CHECK) | Tcode | NBH related Blocked Vendor details we can check in ZMM065 Report | Here to check the blocked vendor related to NBH we need to creted record in ZTMM_VENDOR_BLK table because Zmm065 totally based on this table entry details and Accoding to previous NBH related logic we updating the blocked field of LFA1 & LFM1 database table .so in order to fulfil the business requirment i added code which will crete record in the Vendor block and unbock table. | enhcement Modification | NO | DONE | DEVK947869 :MM:ZMM065:Added new Fields NBH Block | UNO MINDA |  | QAS | 2025-10-09
51 | Rajan singh | MM |  | 2025-09-18 | 18-09-2025` |  | Me21n,me22n(ZCL_IM_6_PO_CUST_CHK -- IF_EX_ME_PROCESS_PO_CUST~CHECK) | Tcode | " | " | enhcement Modification | no | DONE | DEVK947869 :MM:ZMM065:Added new Fields NBH Block | UNO MINDA |  | QAS | 2025-10-09
52 | Rajan singh | MM |  | 2025-09-18 | 2025-09-18 |  | ME31L,ME32L(ZXM06U43) | TCODE | " | " | enhcement Modification | no | DONE | DEVK947869 :MM:ZMM065:Added new Fields NBH Block | UNO MINDA |  | QAS | 2025-10-09
53 | Rajan singh | MM |  | 2025-09-19 | 2025-09-19 |  | ZGATE | TCODE | " | " | Modification | NO | DONE | DEVK947869 :MM:ZMM065:Added new Fields NBH Block | UNO MINDA |  | QAS | 2025-10-09
54 | wajid Chaudhury | MM |  | 2025-09-19 | 2025-09-19 |  | ZMM092 | TCODE | Commenting one samarform Level related Validation due to Production Issue | Here Only I commented some existing code which wa checking level related validation. | Modification | NO | DONE | DEVK947889 9000RUPESH S 8000016356: MM:ZMM092:Label_Scanning_issue_19-9-2025 | UNO MINDA |  | QAS | 2025-09-19
55 | Prveen Kumar | BC |  | 2025-09-20 | 2025-09-20 |  | ZBC010 | Tcode | Retrival of USR Master Tab in ZBC010 process. | Here this USR Master Tab present in program , but due to some internal changes it's revereted to the previous version where USR Master Tab is not available, for that I checked the program whre some one has done the changes which is working correctly, only i have move those edited thing under my TR and chages got reflected. | Modification | No | DONE | DEVK947910 9000RUPESH S 8000016365: BC: User Access Review Improvement | UNO MINDA |  | dev
56 | Rajan singh | mm |  |  |  |  | ZMM122,Z6MM_INVENTORY,Z6MM_INV_EMAIL,ZRMM_DAILY_RRS_STATUS | Tcode & Report |  |  | Modification | no | DONE | DEVK947165 ABAP S 8000015899: MM: Inventory Norms Revised - FG & WI | UNO MINDA |  | qas | 2025-09-22
57 | Bhasker Joshi | QM |  | 2025-09-19 | 2025-09-25 |  | ZGW_QM_TRANSFER_POSTING_DETAIL | ODATA Project | SAP Transfer Posting Data | User can Able to check all the Transfer posting Data of SAP at out side SAP system. | NEW Development | GET | DONE | DEVK947901 9000RUPESH S 8000016360: QM:ODATA:Transfer Posting Master Data | UNO MINDA | ZSANTHUDEV | DEV
58 | Sunil Kumar | mm |  | 2025-09-25 | 374643 |  | zpp177,zpp192 | Tcode | Kitting Process Issue Solution | Kitting Process Issue Solution, for that added some Extra validation to complete the process check. | Modification | no | DONE | DEVK947960 9000RUPESH S 8000016392: PP:Kitting Process Location Changes | UNO MINDA |  |  | 374643
59 | Vivek Mishra | MM |  | 2025-09-25 | 2025-10-06 |  | MIGO(ZCL_IM_Z_MB_MIGO_BADI->IF_EX_MB_MIGO_BADI~CHECK_ITEM) | Tcode Enhacement | SCRAP VALIDATION | SCRAP VALIDATION | Enhacement Modification |  | DONE | DEVK947965 9000RUPESH S 8000016394: MM:SCRAP VALIDATION | UNO MINDA |  | dev | 06-101-2025
60 | Bhasker Joshi | pp |  | 2025-10-06 | 2025-10-07 |  | Z6PM001S_ORDER_CONFIRMATION | Smartform Changes(zpm001) | Addiing LOTO related options in the smartforms | Addiing LOTO related options in the smartforms | Modification | no | DONE | DEVK948011 9000RUPESH S 8000016436: PM:PRNT:ZPM001:check sheet LOTO addition | UNO MINDA |  | QAS | 2025-10-13
61 | AShish Kumar | SD |  | 2025-10-10 | 2025-10-15 |  | ZSD190 | Tcode-New Smartform | Customer Return Delivery Challan | Customer Return Delivery Challan | NEW Development | NO | DONE | DEVK948008 9000RUPESH S 8000016434: SD:RE:Delivery Challan Print | UNO MINDA |  | QAS | 2025-10-31
62 | Ashish Kumar | SD |  | 2025-10-04 | 2025-10-07 |  | ZSD189 | Tcode-Program | FTP Data transfer Program for UML Gujurat | FTP Data transfer Program for UML Gujurat | NEW Development | NO | DONE | DEVK948002 S 8000016427: SD:Invoice Data On FTP_Suzuki_UML_Gujrat | UNO MINDA |  | QAS |  | Shivansh
63 | Sunil Kumar | MM |  | 2025-10-15 | 2025-10-15 |  | ZMM159 | Tcode | MPN * Related logic modification done in ZCL_SGT_CONSOLIDATE_RULES_V1-->GEN_RULES_FOR_A_SEG_STRAT method. | MPN * Issue resolved ,due to which infanite loop issue solved | Modification | NO | Discarded(3-12-2025) | DEVK948082 9000RUPESH S 8000016486: MM:ZMM159:MPN * Issue | UNO MINDA |  |  |  | DebiDutta
64 | Sunil Kumar | PP |  | 2025-10-16 | 16-101-2025 |  | ZPP196 | Tcode | Logic change to meet final business requirement and Performance Tuning | Logic change to meet final business requirement and Performance Tuning | New development Modification | No | DONE | DEVK948613 9000CSUNIL S 8000016813: DOCUMENT DE | UNO MINDA
65 | Anuj Kukreja | SD |  | 2025-10-24 | 2025-10-25 |  | ZGW_SD_PRODUCTLINE | ODATA Project | Provide a API on "ZTSD_PRODUCTLINE" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRODUCTLINE" table , through which we can create,update and delete the record. | New development | GET,POST | DONE | DEVK948119 9000RUPESH S 8000016511: SD:ODATA:Product Line Detail:CUD | UNO MINDA
66 | Anuj Kukreja | SD |  | 2025-10-27 | 2025-10-27 |  | ZGW_SD_PRODUCTFAMILY | ODATA Project | Provide a API on "ZTSD_PRDTFAMILY" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRDTFAMILY" table , through which we can create,update and delete the record. | New Development | GET,POST | DONE | DEVK948138 9000RUPESH S 8000016529: SD:OData:Product Family:CRUD | UNO MINDA
67 | Anuj Kukreja | SD |  | 2025-10-28 | 2025-10-28 |  | ZGW_SD_PRODUCT | ODATA Project | Provide a API on "ZTSD_PRODUCT" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRODUCT" table , through which we can create,update and delete the record. | New Development | GET,POST | DONE | DEVK948140 9000RUPESH S 8000016531: SD:OData:Product:CRUD | UNO MINDA
68 | Sunil kumar | pp | 2025-10-13 | 2025-10-29 | 2025-10-30 | 1st(69 development is depend upon this) | ZPP_BOM_FGHEADER_UPLOAD | Report Program(ZPP197) | Create a cheduler which will upload FG Header material's and its Componets in a Custom Table(ztpp_BOMFGHeader). | Create a cheduler which will upload FG Header material's and its Componets in a Custom Table(ztpp_BOMFGHeader).This development happened as per Functional FS.S | NEW Development | NO | DONE | DEVK948157 9000RUPESH S 8000016551: PP:BOM Header Upload in Custom Table | UNO MINDA |  | QAS | 2025-12-16 | DEBI
69 | Sunil Kumar | pp |  | 2025-10-30 | 2025-11-03 | 2nd(Don't Move befor moving the 68 no object to PRD) | ZGW_PP_FGMATERIAL_DETAILS | ODATA Project | Create GET API for fetch the BOM FG Header material along with the Componet. | Create GET API for fetch the BOM FG Header material along with the Componet. | NEW Development | GET | DONE | DEVK948174 9000RUPESH S 8000016560: PP:ODATA:BOM FG Header Material | UNO MINDA
70 | Anuj Kukreja | SD |  | 2025-11-03 | 2025-11-04 | Product Detail Report | ZSD124R | Report Program(ZSD124R) | This Report will give the Product details. | This Report will give the Product details. | New Development | No | DONE | DEVK948186 9000RUPESH S 8000016567: SD:REPT:Product Detail | Uno Minda |  |  | 2025-11-10
71 | ashish Kumar | SD |  | 2025-11-05 | 2025-11-07 |  | ZSD190,ZSD190R | Smartform Changes and New Delivery report | Allignment in Samrtform and added new design along with develop a new report through which user can get the Delivery challan number against the Sales order number with Place or=f dispatch address. | Allignment in Samrtform and added new design along with develop a new report through which user can get the Delivery challan number against the Sales order number with Place or=f dispatch address. | Modification,New Development | no | DONE | DEVK948236 9000RUPESH S 8000016593: SD: Delivery Challan Logo Logic Add | UNO MINDA
72 | Sunil Kumar | PP |  | 2025-11-10 | 2025-11-12 |  | ZGW_PP_ROUTING_COST_CENTER | ODATA Project | User will get the Routing Cost Center Details | User will get the Routing Cost Center Details | new Development | Get | DONE | DEVK948286 9000RUPESH S 8000016624: PP:ODATA:Routing Cost Center | UNO MINDA
74 | Sunil Kumar | MM | 2025-11-12 | 2025-11-14 | 2025-11-19 | SAP PURCHASE ORDER GOODS RECIEPT | ZGW_MM_PO_GR_POSTING | ODATA Project | Through this API business user can post/DO GRN & Create material Document in sap system. | Through this API business user can post/DO GRN & Create material Document in sap system. | new Development | POST | DONE | DEVK948318 9000RUPESH S 8000016640: MM:ODATA:PO GR Posting | UNO MINDA
75 | Rupesh Chauhan | PP |  | 2025-11-19 | 2025-11-20 |  | ZPP176 | Report(ZRPP_ECMS_BOM_REPORT) | Adding Logic for Bill of material,Bomusage & designater-3 Field Value.Due to this End user can easily access those data. | Adding Logic for Bill of material,Bomusage & designater-3 Field Value. | Modification | No | DONE | DEVK948370 9000RUPESH S 8000016667: PP:BOM Report :ZPP176:Designator change | UNO MINDA |  |  | 2025-11-21
76 | Rupesh Chauhan | QM | 2025-11-19 | 2025-11-25 | 2025-11-27 | SAP Defactive Type Data | ZGW_QM_DEFECT_TYPE_DATA | ODATA Project | Through this API business user Check The SAP Defactive type details. | Through this API business user Check The SAP Defactive type details. | New Development | GET | DONE | DEVK948408 9000RUPESH S 8000016693: QM:ODATA:Defect Type Data | UNO MINDA |  |  |  | sayan
77 | Siddharth Tiwari | FI | 2025-11-21 | 2025-11-21 | 2025-11-21 | RTGS - SMARTFORM | ZFI_RFFOUS_RTGS_ADV | PRINT | User can check the Not coming Document Numbers in the Print | User can check the Not coming Document Numbers in the Print | Modification | No | Done | DEVK948387 9000RUPESH S 8000016678: FICO: Payment Advice Smartform Changes | UNO MINDA |  |  | 2025-11-21 | Debi
78 | Anuj Kukreja | SD | 2025-11-27 | 2025-12-01 | 2025-12-03 | Condition pricing value of material w.r.t plant for Budget preparation | ZSD141B | Report | User can Check Condition pricing value of material w.r.t plant for Budget preparation Details in ALV Report Formart | User can Check Condition pricing value of material w.r.t plant for Budget preparation Details in ALV Report Formart | New Development | No | Done | DEVK948478 9000RUPESH S 8000016733: SD:Condition pricing value of material | UNO MINDA | ZSD01 |  |  | SAYAN
79 | Sunil Kumar | MM | 2025-11-28 | 2025-12-04 | 2025-12-06 | SAP GRN Gate Entry API | ZGW_MM_GRN_GATEENTRY | ODATA Project | Here User can check all the existing Gate entry details on which GRN is not done yet. | Here User can check all the existing Gate entry details on which GRN is not done yet. | New Development | GET | Done | DEVK948512 9000RUPESH S 8000016752: MM:ODATA:GRN Gate Entry Details | UNO MINDA | ZSANTHUDEV | QAS | 2025-12-16 | SAYAN
80 | Pradeep Chaudhury | MM | 2025-12-09 | 2025-12-10 | 2025-12-10 | PR Smartform issue at PRD | ZMM023 | smartform(Z6MM023S_PUR_REQUISITION) | Here user can able to check correct Gross price in Smartform | Here user can able to check correct Gross price in Smartform Because the field which showing gross price at smartform level, there is no currency & quantity reference control done at print level, so here I added those currency code field with the variable field level and got the solution of issue | Modification | NO | Done | DEVK948569 9000RUPESH S 8000016783: MM:SMARTFORMS: PR Price Issue Changes | UNO MINDA(PRD SANDBOX) |  | QAS | 2025-12-12 | SAYAN
81 | Sunil kumar | PP | 2025-12-15 | 2025-12-16 |  | Material Transfer Based on Production Order |  | Report |  |  | New Developmet | No | in progress | DEVK948599 S 8000016801: PP:REPORTS:Material Transfer Prod Ord | UNO Minda | ZSANTUDEV | DEV |  | SAYAN
82 | Sanjeev Kumar | SD | 2025-12-16 |  |  | NFR Mapping Validation

## API
SL NO | Business user | Module | Email Recived Date | Development Start Date | Completion Date at Development | Object Description | Object | Object Service Name | Type | Benefits | Details | Development Type | API Call | Status | Transport Request(Workbench TR)-Minda server | Transport Request(Workbench TR)-Minda Gateway server | System | Package | TR status | Date of Mail for TR to quality : Minda Server | Date of Mail for TR to quality : Minda Gateway Server | Person Worked | FS Document Name | TS Document Name
1 | Rupesh Chauhan | PP |  | 2026-06-26 | 2025-06-30 | SAP ROUTING DETAILS | ZGW_PP_ROUTING_DETAIL | ZGW_PP_ROUTING_DETAIL_SRV | ODATA Project | Routing Details | Here for getting routing details user o need to check multiple Tables as well as we can show SAP routing Details in outside SAP system Thouth ODATA API call. | NEW Development | GET | DONE | DEVK947001 9000RUPESH S 8000015789: PP:ODATA:SAP Routing Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_ROUTING_DETAILS | TS_PP_Routing Data
2 | Rupesh Chauhan | PP |  | 2025-06-25 | 2025-07-04 | SAP PRODUCTION VERSION | ZGW_PP_PRODUCTION_VERSION | ZGW_PP_PRODUCTION_VERSION_SRV | ODATA Project | Production Version Details | Provided GET API to fetch Production Version Details. | NEW Development | GET | DONE | DEVK947047 9000RUPESH S 8000015826: PP:ODATA:SAP Production Version Detail | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | Shivansh | FS_PP_SAP_PRODUCTION VERSION | TS_PP_Production Version
3 | Rupesh Chauhan | PP |  | 2025-07-04 | 2025-07-09 | SAP Production Order Data | ZGW_PP_PRODUCTION_ORDER | ZGW_PP_PRODUCTION_ORDER_SRV | ODATA Project | Production Order Details | Provided GET API to fetch Production Order Details Along with Get the Routing & component Details per production Order. | NEW Development | GET | DONE | DEVK947147 9000RUPESH S 8000015885: PP:ODATA:SAP Production Order Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_PRODUCTION ORDER | TS_PP_Production order
4 | Rupesh Chauhan | PP |  | 2025-07-10 | 2025-07-14 | PRODUCTION ORDER CONFIRMATION WITHOUT MPN | ZGW_PP_PRDC_CONF_WITHOUT_MPN | ZGW_PP_PRDC_CONF_WITHOUT_MPN_SRV | ODATA Project | Production Order Confirmation Without MPN | User can send a production order confirmation without MPN Create Send Request from Outside SAP Application and based on the Request, it will crete record in SAP System. | NEW Development | POST | DONE | DEVK947192 9000RUPESH S 8000015910: PP:ODATA: Production Conf. Without MPN | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_ORDER CONFIRMATION WITHOUT MPN | TS_PP_Production Confirmation Without MPN_POST
5 | Rupesh Chauhan | PP |  | 2025-07-14 | 2025-07-18 | SAP TRANSFER POSTING | ZGW_PP_PRDC_ORD_TRANS_POSTING | ZGW_PP_PRDC_ORD_TRANS_POSTING_SRV | ODATA Project | Transfer Posting | User can send Material tranfer posting from outside SAP system and based on the request it will create record in SAP System. | NEW Development | POST | DONE | DEVK947217 9000RUPESH S 8000015929: PP:ODATA:Production Order TransferPostig | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_TRANSFER POSTING | TS_PP_Transfer_Posting_POST
6 | Rupesh Chauhan | PP |  | 2025-07-21 | 2025-07-24 | SAP BOM Detais | ZGW_PP_BOM_DETAIL | ZGW_PP_BOM_DETAIL_SRV | ODATA Project | BOM Master Details | User can able tho see the BOM details along | NEW Development | GET | DONE | DEVK947283 9000RUPESH S 8000015973: PP:ODATA: Bill Of Material(BOM) Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_BOM | TS_MM_Bom_Master_Details
7 | Rupesh Chauhan | MM |  | 2025-07-28 | 2025-07-31 | SAP Material Master API | ZGW_MM_MATERIAL_MASTER_DETAIL | ZGW_MM_MATERIAL_MASTER_DETAIL_SRV | ODATA Project | Material Master Details | User Can able to See Material Master details outside of SAP Server/System | NEW Development | GET | Done | DEVK947359 9000RUPESH S 8000016007: MM:ODATA: Material Master Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS MATERIAL MASTER V1 FS_MM_MATERAIL_MLAN V2 | TS_MM_Material master details
8 | Sunil Kumar | PP |  | 2025-08-06 | 2025-08-08 | SAP PRODUCTION GOODS ISSUE | ZGW_PP_PRODUCTION_GOODS_ISSUE | ZGW_PP_PRODUCTION_GOODS_ISSUE_SRV | ODATA Project | Production Goods Issue | User can issue the goods against Production order from Outside SAP System | NEW Development | POST | Done | DEVK947507 9000RUPESH S 8000016113: PP:ODATA:Production Goods Issue | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_PP_SAP_GOODS ISSUE | TS_PP_Productions_goods_issue_POST
9 | Sunil Kumar | MM |  | 2025-08-13 | 2025-08-19 | SAP BATCH MANAGEMENT DATA | ZGW_MM_BATCH_MANAGEMENT | ZGW_MM_BATCH_MANAGEMENT_SRV | ODATA Project | SAP Batch management DATA | End user can access Material Batch details outside of SAP Environment. | NEW Development | GET | Done | DEVK947589 9000RUPESH S 8000016162: MM:ODATA:Batch Management Data | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_MM_BATCH MANAGEMENT | TS_MM_BATCH_MANAGEMENT_DATA
10 | Wajid Chaudhury/Vivek | MM |  | 2025-08-25 | 2025-08-27 | SAP MIGO DATA | ZGW_MM_MIGO_DETAILS | ZGW_MM_MIGO_DETAILS_SRV | ODATA Project | SAP MIGO Data | End user can access SAP MIGO Data outside of SAP Environment. | NEW Development | GET | Done | DEVK947680 9000RUPESH S 8000016221: MM:ODATA:MM:MIGO Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_MM_MIGO | TS_MM_MIGO_Data
11 | Wajid Chaudhury/Vivek | MM |  | 2025-09-01 | 2025-09-08 | SAP Vendor master Details | ZGW_MM_VENDOR_MASTER_DETAIL | ZGW_MM_VENDOR_MASTER_DETAIL_SRV | ODATA Project | SAP Vendor Master Data | End User Can Access SAP Vendor Master Data from Outside SAP Environment. | NEW Development | GET | DONE | DEVK947733 9000RUPESH S 8000016264: MM:ODATA:Vendor Mater Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_MM_VENDOR_DATA | TS_MM_Vendor_Master_data
12 | Sunil Kumar/Ashish Kumar | SD |  | 2025-03-12 | 2025-09-18 | SAP Delivery Master Data | ZGW_SD_DELIVERY_DETAILS | ZGW_SD_DELIVERY_DETAILS_SRV | ODATA Project | SAP Delivery Master Data | End User can access SAP delivery Master Data Outside SAP | NEW Development | GET | DONE | DEVK947845 9000RUPESH S 8000016327: SD:ODATA:Delivery Master Data | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | Availabl in TS_SD_Delivery_Mster_Data | TS_SD_Delivery_Mster_Data
13 | Bhasker Joshi | QM |  | 2025-09-19 |  | SAP QM Transfer posting | ZGW_QM_TRANSFER_POSTING_DETAIL | ZGW_QM_TRANSFER_POSTING_DETAIL_SRV | ODATA Project | SAP Transfer Posting Data | User can Able to check all the Transfer posting Data of SAP at out side SAP system. | NEW Development | GET | DONE | DEVK947901 9000RUPESH S 8000016360: QM:ODATA:Transfer Posting Master Data | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS Transfer posting (321, 322, 349 & 350 Movement type) TEST CASE MSEG data for 321, 322 , 349 & 350 | TS_QM_Transfer_Posting_Data
14 | Anuj Kukreja | SD |  | 2025-10-24 | 2025-10-25 | Product Line Custom Table CUD Operation | ZGW_SD_PRODUCTLINE | ZGW_SD_PRODUCTLINE_SRV | ODATA Project | Provide a API on "ZTSD_PRODUCTLINE" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRODUCTLINE" table , through which we can create,update and delete the record. | New development | GET,POST | DONE | DEVK948119 9000RUPESH S 8000016511: SD:ODATA:Product Line Detail:CUD | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | NA | TS_ODATA_PRODUCT_LINE_CRUD
15 | Anuj Kukreja | SD |  | 2025-10-27 | 2025-10-27 | Product Family Custom Table CRUD Operation | ZGW_SD_PRODUCTFAMILY | ZGW_SD_PRODUCTFAMILY_SRV | ODATA Project | Provide a API on "ZTSD_PRDTFAMILY" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRDTFAMILY" table , through which we can create,update and delete the record. | New Development | GET,POST | DONE | DEVK948138 9000RUPESH S 8000016529: SD:OData:Product Family:CRUD | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | NA | TS_ODATA_PRODUCT_FAMILY_CRUD
16 | Anuj Kukreja | SD |  | 2025-10-28 | 2025-10-28 | Product Custom Table CRUD Operation | ZGW_SD_PRODUCT | ZGW_SD_PRODUCT_SRV | ODATA Project | Provide a API on "ZTSD_PRODUCT" table , through which we can create,update and delete the record. | Provide a API on "ZTSD_PRODUCT" table , through which we can create,update and delete the record. | New Development | GET,POST | DONE | DEVK948140 9000RUPESH S 8000016531: SD:OData:Product:CRUD | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | NA | TS_ODATA_PRODUCT_CRUD
17 | Sunil Kumar | pp |  | 2025-10-30 | 2025-11-03 | BOM FG Header Material Details | ZGW_PP_FGMATERIAL_DETAILS | ZGW_PP_FGMATERIAL_DETAILS_SRV | ODATA Project | Create GET API for fetch the BOM FG Header material along with the Componet. | Create GET API for fetch the BOM FG Header material along with the Componet. | NEW Development | GET | DONE | DEVK948174 9000RUPESH S 8000016560: PP:ODATA:BOM FG Header Material |  | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-20 |  | DEBI | FS_PP_API FOR BOM HEADER FIND | TS_PP_BOM_FG_MATERIAL_DETAILS
18 | Sunil Kumar | PP |  | 2025-11-10 | 2025-11-12 | SAP Routing Cost Center Details | ZGW_PP_ROUTING_COST_CENTER | ZGW_PP_ROUTING_COST_CENTER_SRV | ODATA Project | User will get the Routing Cost Center Details | User will get the Routing Cost Center Details | New Development | Get |  | DEVK948286 9000RUPESH S 8000016624: PP:ODATA:Routing Cost Center | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | Availabl in TS_PP_Routing_cost_center | TS_PP_Routing_cost_center
19 | Sunil Kumar | MM | 2025-11-12 | 2025-11-14 | 2025-11-19 | SAP PURCHASE ORDER GOODS RECIEPT | ZGW_MM_PO_GR_POSTING | ZGW_MM_PO_GR_POSTING_SRV | ODATA Project | Through this API business user can post/DO GRN & Create material Document in sap system. | Through this API business user can post/DO GRN & Create material Document in sap system. | New Development | POST | DONE | DEVK948318 9000RUPESH S 8000016640: MM:ODATA:PO GR Posting | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV | DEV | 2025-12-10 | 2025-12-16 | DEBI | FS_MM_SAP_GOODS RECIEPT | TS_MM_SAP_PURCHASE_ORDER_GOODS_RECIEPT_POST
20 | Rupesh Chauhan | QM | 2025-11-19 | 2025-11-25 | 2025-11-27 | SAP Defactive Type Data | ZGW_QM_DEFECT_TYPE_DATA | ZGW_QM_DEFECT_TYPE_DATA_SRV | ODATA Project | Through this API business user Check The SAP Defactive type details. | Through this API business user Check The SAP Defactive type details. | New Development | GET | DONE | DEVK948408 9000RUPESH S 8000016693: QM:ODATA:Defect Type Data |  | UNO MINDA | ZSANTHUDEV | DEV |  |  | Sayan | FS of Defect type- QPR | TS_QM_Defective_Type_Data
21 | Sunil Kumar | MM | 2025-11-28 | 2025-12-04 | 2025-12-06 | SAP GRN Gate Entry API | ZGW_MM_GRN_GATEENTRY | ZGW_MM_GRN_GATEENTRY_SRV | ODATA Project | Here User can check all the existing Gate entry details on which GRN is not done yet. | Here User can check all the existing Gate entry details on which GRN is not done yet. | New Development | GET | Done | DEVK948512 9000RUPESH S 8000016752: MM:ODATA:GRN Gate Entry Details | GWDK900414 ODATA:Workbanch:gateway API Register GWDK900417 ODATA:Customizing:gateway API Register Alias | UNO MINDA | ZSANTHUDEV |  | 2025-12-16 | 2025-12-16 | SAYAN | FS_MM_GATE | TS_MM_GRN_GATEENTRY

## ODATA API LIST Moved to Quality
Object Description | Transport Request(Workbench TR)-Minda server | Workbench TR - Minda Gateway Server | Cutomizing TR - Minda Gateway Server
SAP ROUTING DETAILS | DEVK947001 9000RUPESH S 8000015789: PP:ODATA:SAP Routing Details | GWDK900414 9000RUPESH ODATA:Workbanch:gateway API Register | GWDK900417 100 9000RUPESH ODATA:Customizing:gateway API Register Alias
SAP PRODUCTION VERSION | DEVK947047 9000RUPESH S 8000015826: PP:ODATA:SAP Production Version Detail
SAP Production Order Data | DEVK947147 9000RUPESH S 8000015885: PP:ODATA:SAP Production Order Details
PRODUCTION ORDER CONFIRMATION WITHOUT MPN | DEVK947192 9000RUPESH S 8000015910: PP:ODATA: Production Conf. Without MPN
SAP TRANSFER POSTING | DEVK947217 9000RUPESH S 8000015929: PP:ODATA:Production Order TransferPostig
SAP BOM Detais | DEVK947283 9000RUPESH S 8000015973: PP:ODATA: Bill Of Material(BOM) Details
SAP Material Master API | DEVK947359 9000RUPESH S 8000016007: MM:ODATA: Material Master Details
SAP PRODUCTION GOODS ISSUE | DEVK947507 9000RUPESH S 8000016113: PP:ODATA:Production Goods Issue
SAP BATCH MANAGEMENT DATA | DEVK947589 9000RUPESH S 8000016162: MM:ODATA:Batch Management Data
SAP MIGO DATA | DEVK947680 9000RUPESH S 8000016221: MM:ODATA:MM:MIGO Details
SAP Vendor master Details | DEVK947733 9000RUPESH S 8000016264: MM:ODATA:Vendor Mater Details
SAP Delivery Master Data | DEVK947845 9000RUPESH S 8000016327: SD:ODATA:Delivery Master Data
SAP QM Transfer posting | DEVK947901 9000RUPESH S 8000016360: QM:ODATA:Transfer Posting Master Data
Product Line Custom Table CUD Operation | DEVK948119 9000RUPESH S 8000016511: SD:ODATA:Product Line Detail:CUD
Product Family Custom Table CRUD Operation | DEVK948138 9000RUPESH S 8000016529: SD:OData:Product Family:CRUD
Product Custom Table CRUD Operation | DEVK948140 9000RUPESH S 8000016531: SD:OData:Product:CRUD
SAP Routing Cost Center Details | DEVK948286 9000RUPESH S 8000016624: PP:ODATA:Routing Cost Center
SAP PURCHASE ORDER GOODS RECIEPT | DEVK948318 9000RUPESH S 8000016640: MM:ODATA:PO GR Posting
SAP GRN Gate Entry API | DEVK948512 9000RUPESH S 8000016752: MM:ODATA:GRN Gate Entry Details
BOM FG Header Material Details | DEVK948174 9000RUPESH S 8000016560: PP:ODATA:BOM FG Header Material | GWDK900419 | GWDK900421

## KT to Sayan
SL NO | Business user | Module | Object Description | Object(SEGW Project Name/Repot/Tcode) | Type | Development Type | API Call | Status | FS Document Name | TS Document Name | Status | KT Complition Date
1 | Rupesh Chauhan | PP | SAP ROUTING DETAILS | ZGW_PP_ROUTING_DETAIL | ODATA Project | NEW Development | GET | DONE | FS_PP_SAP_ROUTING_DETAILS | TS_PP_Routing Data | DONE | 2025-11-25
2 | Rupesh Chauhan | PP | SAP PRODUCTION VERSION | ZGW_PP_PRODUCTION_VERSION | ODATA Project | NEW Development | GET | DONE | FS_PP_SAP_PRODUCTION VERSION | TS_PP_Production Version | DONE | 2025-11-26
3 | Rupesh Chauhan | PP | SAP Production Order Data | ZGW_PP_PRODUCTION_ORDER | ODATA Project | NEW Development | GET | DONE | FS_PP_SAP_PRODUCTION ORDER | TS_PP_Production order | DONE | 2025-11-26
4 | Rupesh Chauhan | PP | PRODUCTION ORDER CONFIRMATION WITHOUT MPN | ZGW_PP_PRDC_CONF_WITHOUT_MPN | ODATA Project | NEW Development | POST | DONE | FS_PP_SAP_ORDER CONFIRMATION WITHOUT MPN | TS_PP_Production Confirmation Without MPN_POST | DONE | 2025-11-27
5 | Rupesh Chauhan | PP | SAP TRANSFER POSTING | ZGW_PP_PRDC_ORD_TRANS_POSTING | ODATA Project | NEW Development | POST | DONE | FS_PP_SAP_TRANSFER POSTING | TS_PP_Transfer_Posting_POST | DONE | 2025-11-27
6 | Rupesh Chauhan | PP | SAP BOM Details | ZGW_PP_BOM_DETAIL | ODATA Project | NEW Development | GET | DONE | FS_PP_SAP_BOM | TS_MM_Bom_Master_Details | DONE | 2025-11-28
7 | Rupesh Chauhan | MM | SAP Material Master API | ZGW_MM_MATERIAL_MASTER_DETAIL | ODATA Project | NEW Development | GET | DONE | FS MATERIAL MASTER V1 FS_MM_MATERAIL_MLAN V2 | TS_MM_Material master details | DONE | 2025-12-02
8 | Sunil Kumar | PP | SAP PRODUCTION GOODS ISSUE | ZGW_PP_PRODUCTION_GOODS_ISSUE | ODATA Project | NEW Development | POST | DONE | FS_PP_SAP_GOODS ISSUE | TS_PP_Productions_goods_issue_POST | DONE | 2025-11-27
9 | Sunil Kumar | MM | SAP BATCH MANAGEMENT DATA | ZGW_MM_BATCH_MANAGEMENT | ODATA Project | NEW Development | GET | DONE | FS_MM_BATCH MANAGEMENT | TS_MM_BATCH_MANAGEMENT_DATA | DONE | 2025-12-02
10 | Wajid Chaudhury/Vivek | MM | SAP MIGO DATA | ZGW_MM_MIGO_DETAILS | ODATA Project | NEW Development | GET | DONE | FS_MM_MIGO | TS_MM_MIGO_Data | DONE | 2025-12-04
11 | Wajid Chaudhury/Vivek | MM | SAP Vendor master Details | ZGW_MM_VENDOR_MASTER_DETAIL | ODATA Project | NEW Development | GET | DONE | FS_MM_VENDOR_DATA | TS_MM_Vendor_Master_data | DONE | 2025-12-05
12 | Sunil Kumar/Ashish Kumar | SD | SAP Delivery Master Data | ZGW_SD_DELIVERY_DETAILS | ODATA Project | NEW Development | GET | DONE | Availabl in TS_SD_Delivery_Mster_Data | TS_SD_Delivery_Mster_Data | DONE | 2025-12-05
13 | Bhasker Joshi | QM | SAP QM Transfer posting | ZGW_QM_TRANSFER_POSTING_DETAIL | ODATA Project | NEW Development | GET | DONE | FS Transfer posting (321, 322, 349 & 350 Movement type) TEST CASE MSEG data for 321, 322 , 349 & 350 | TS_QM_Transfer_Posting_Data | DONE | 2025-12-04
14 | Anuj Kukreja | SD | Product Line Custom Table CUD Operation | ZGW_SD_PRODUCTLINE | ODATA Project | NEW Development | GET,POST | DONE | Available in TS_ODATA_PRODUCT_LINE_CRUD | TS_ODATA_PRODUCT_LINE_CRUD | DONE | 2025-11-28
15 | Anuj Kukreja | SD | Product Family Custom Table CRUD Operation | ZGW_SD_PRODUCTFAMILY | ODATA Project | NEW Development | GET,POST | DONE | Available in TS_ODATA_PRODUCT_FAMILY_CRUD | TS_ODATA_PRODUCT_FAMILY_CRUD | DONE | 2025-11-28
16 | Anuj Kukreja | SD | Product Custom Table CRUD Operation | ZGW_SD_PRODUCT | ODATA Project | NEW Development | GET,POST | DONE | Available in TS_ODATA_PRODUCT_CRUD | TS_ODATA_PRODUCT_CRUD | DONE | 2025-11-28
17 | Sunil kumar | PP | FG Material Upload in Custom Table | ZPP197 | Background Job Report | NEW Development |  | DONE | FS_PP_API FOR BOM HEADER FIND | NA | DONE | 2025-12-03
18 | Sunil Kumar | pp | BOM FG Header Material Details | ZGW_PP_FGMATERIAL_DETAILS | ODATA Project | NEW Development | GET | DONE | FS_PP_API FOR BOM HEADER FIND | TS_PP_BOM_FG_MATERIAL_DETAILS | DONE | 2025-12-03
19 | Sunil Kumar | PP | SAP Routing Cost Center Details | ZGW_PP_ROUTING_COST_CENTER | ODATA Project | NEW Development | GET | DONE | Availabl in TS_PP_Routing_cost_center | TS_PP_Routing_cost_center | DONE | 2025-12-05
20 | Sunil Kumar | MM | SAP PURCHASE ORDER GOODS RECIEPT | ZGW_MM_PO_GR_POSTING | ODATA Project | NEW Development | POST | DONE | FS_MM_SAP_GOODS RECIEPT | TS_SAP_PURCHASE_ORDER_GOODS_RECIEPT_POST | DONE | 2015-11-18
21 | Anuj Kukreja | SD | Product Detail Report | ZSD124R | ALV Report | NEW Development | No | DONE | NA | NA | DONE | 2025-12-08
22 | AsHish Kumar | SD | Delivery Clallan Print | ZSD190 | ALV Report + Print | NEW Development | NO | DONE | FS_SD_Delivery Challan Changes print | NA | DONE | 2025-12-10